## 10h30
MEETING MINUTES
Project Code: |  |  |  | Conductor: |  |  | Date: | 2018-01-09
Project Manager: |  | Nguyễn Huy Hùng |  | Secretary: | Trần Hồ Minh Thuấn |  | Venue:
LIST OF ATTENDEES
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Nguyễn Huy Hùng |  |  |  |  | Project Manager |  | Present
2 | Nguyễn Việt Tú |  |  |  | 11 | Leader |  | Present
3 | Hoàng Quốc Việt |  |  |  | 11 | Member |  | Present
4 | Thái Tiến Hoàng |  |  |  | 11 | Member |  | Present
5 | Trần Hồ Minh Thuấn |  |  |  | 11 | Member |  | Present
AGENDA
- Assgins task for team in week 1. - Question about requirement.
CONTENT
Mr. Hung assigns tasks for team in week 1 (from 09/01/2018 to 16/01/2018), which includes: - Create Product Backlog - Mockup UI - ERD - Overview UseCase - Create report 1 At the rest of the meeting, team members ask Mr.Hung some questions about requirement to make it clearly. Some questions in meeting: - Quan hệ giữa role và user trong phân quyền động - Chi tiết về chức năng Set interval time - Remind undone feedback được gửi sau khi hết interval time hay gần khi interval time kết thúc - Feedback là ai cũng gửi đc hay chỉ sinh viên Detail requirements: - Users (with any role) can + conduct feedbacks for courses/ lecturer/ department + View their feedbacks history - Lecturer inherit basic user's functions and can view results & reports of feedbacks for them/ sent to them by staff - Staff inherit all Lecturer's functions and can + Manage feedback/ template (CRUD, customize feedback form chosen template, publish feedback) + Choose user who can view results & report of feedbacks + Remind users to conduct undone feedbacks - Head of Academic inherit all Staff's functions & can + Manage role (CRUD, set role permissions) + Manage system's users (CRUD, change status ...)
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
Note on L42: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M42: Fill the date if needed. Otherwise, leave the cell 'BLANK'