## General
MEETING MINUTES
Project Code: |  |  |  | Conductor: |  |  | Date: | 2018-01-10
Project Manager: |  | Nguyễn Huy Hùng |  | Secretary: | Trần Hồ Minh Thuấn |  | Venue:
LIST OF ATTENDEES
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Nguyễn Việt Tú |  |  |  | 11 | Leader |  | Present
2 | Hoàng Quốc Việt |  |  |  | 11 | Member |  | Present
3 | Thái Tiến Hoàng |  |  |  | 11 | Member |  | Present
4 | Trần Hồ Minh Thuấn |  |  |  | 11 | Member |  | Present
AGENDA
- Assgins tasks for team in week 1. - Question about requirement.
CONTENT
At the rest of the meeting, team members decided to ask Mr.Hung some questions on next review day about requirement to make it clearly: - How do we set interval time & remind user too conduct undone feedbacks - Analyze & send report after feedback closed (after available time ends) or everytime user request to get report based on received results Decisions after meetings: - Use SrarUML for all UML Diagrams - Docs - Use Justinmind for designing mockups - Report 1 Docs & Product backlog were assigned by Tú & will be reviewed by all team's members - Assign Sprint 1's tasks for members: Thuấn & Việt design UCD, Tú & Hoàng design ERD. Mockups' tasks were assigned by Tú, Việt, Thuấn. Details of tasks on Trello https://trello.com/b/0CjmiCVK/sprint-1 & Sprint backlogs https://docs.google.com/spreadsheets/u/1/d/1Tj9tsbnGwQrQiTGnWU0NW55C2mwtRrxtwqqfhS-2teA/edit#gid=0
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
Note on L41: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M41: Fill the date if needed. Otherwise, leave the cell 'BLANK'