## General
MEETING MINUTES
Project Code: |  |  |  | Conductor: |  |  | Date: | 2018-01-15
Project Manager: |  | Nguyễn Huy Hùng |  | Secretary: | Trần Hồ Minh Thuấn |  | Venue:
LIST OF ATTENDEES
No | Full Name |  |  |  | Unit/Group | Position |  | Attendance
1 | Nguyễn Huy Hùng |  |  |  |  | Project Manager |  | Present
2 | Nguyễn Việt Tú |  |  |  | 11 | Leader |  | Present
3 | Hoàng Quốc Việt |  |  |  | 11 | Member |  | Present
4 | Thái Tiến Hoàng |  |  |  | 11 | Member |  | Late
5 | Trần Hồ Minh Thuấn |  |  |  | 11 | Member |  | Present
AGENDA
- Assgins task for team in week 2. - Question about requirement.
CONTENT
Mr. Hung assigns tasks for team in week 2 (from 15/01/2018 to 23/01/2018), which includes: - Create Product Backlog - Add Sprint Backlog - Mockup UI - ERD - Overview UseCase - Create report 1 At the rest of the meeting, team members ask Mr.Hung some questions about requirement to make it clearly. Some questions in meeting: - Mở rộng scope của hệ thống: đưa ra suggestion thông qua hành vi người dùng & thông qua các trường hợp đề xuất trc do staff - Remind user to conduct undone feedbacks after interval time off feedbacks ended or before? Detail requirements: - Product backlog phải dựa theo template trong excel - Bổ sung Sprint backlog, track lại mức độ hoàn thành task thay đổi theo thời gian (ngày/ thời điểm cập nhật task) trong sprint - Mockup UI must focus on main functions' screens and display practical static data - Fix ERD for easy access & data mining, remove the foreign keys (not neccessary in ERD) - Fix Overview UseCase (add Report functions' usecases)
CONCLUSION
No | Discussed Items |  | Decisions |  |  |  |  | PIC | Deadline
Note on L42: Fill the name of PIC (Person-in-charge) if needed. Otherwise, leave the cell 'BLANK'
Note on M42: Fill the date if needed. Otherwise, leave the cell 'BLANK'